## Ann 9 A plan
Annex 9 Country action plan 2 years
Calendar of activities
N° | Activities | Q1 | Q2 | Q3 | Q4 | Q5 | Q6 | Q7 | Q8 | R1 | R2 | Budget | Contribution | Observation
1 | Supply sourcing | [10 empty] | 0
1.1 | Prepare a listing of the registered suppliers for all pharmaceuticals included in the procurement plans for GF grants | X |  |  |  | X |  |  |  | PMU | NDRA | 0
1.2 | Regular updating of this list of registered suppliers |  | X |  |  |  | X |  |  | PMU | NDRA | 0
1.3 | Prepare issuing of temporary waivers by NDRA | X |  |  |  |  | X |  |  | PMU | NDRA | 0
1.4 | Prepare a briefing for suppliers of non registered drugs on the fast track procedures and costs for registration of drugs | X | [7 empty] | PMU | NDRA | 0
2 | Transport requirements | [10 empty] | 1000
2.1 | Adaptation of tender/procurement documents in relation to QA related freight requirements | X | [7 empty] | PMU |  | 0
2.2 | Revision & Update on the freight requirements |  |  | X |  |  | X |  |  | PMU |  | 0
2.3 | Analyse overall data (refer 4.3) on transport conditions and proceed with relevant follow up actions |  |  | X |  |  |  | X |  | QA task force |  | 1000 | 80 % UNDP, 20 % MoH | R7 and R8 grants
3 | Transit | [10 empty] | 500
3.1 | Evaluation of the storage conditions at the port of entry (warehouses at the airport). | X |  |  |  |  | X |  |  | NDRA | PMU | 500
4 | Receiving | [10 empty] | 1500
4.1 | Reception of the consignments according to the SoP |  | X | X | X | X | X | X | X | Medical stores | Medical stores, PR, NDRA | 0
4.2 | Preparation of the receiving report |  | X | X | X | X | X | X | X | Medical stores | Medical stores, PR, NDRA | 0
4.3 | Verification of the data loggers & individual follow up action. |  | X | X | X | X | X | X | X | Medical stores | Medical stores, PR, NDRA | 0
4.4 | Reporting on any discrepancies on the recieved consignments within 24hours |  | X | X | X | X | X | X | X | Medical stores | Medical stores, PR, NDRA | 0
4.5 | Sampling of consignments at receiving |  | X | X | X | X | X | X | X | Medical stores | NDRA | 0
4.6 | Evaluation of the results of receiving: volume and specs discrepencies, noted and confirmed QC problem. |  |  |  |  | X |  |  |  | QA task force |  | 500 | R7 TB
4.7 | Adaptation of receiving SOP and information provided to relevant sections of PMU and partners |  |  |  |  | X | X |  |  | QA task force | Medical stores | 1000 | R7 TB
5 | Quality control for pharmaceuticals & non-pharmaceuticals | [10 empty] | 3000
5.1 | Prepare an annual sampling plan |  | X |  |  | X |  |  |  | PMU | NDRA & PSO | 3000 | R8 Mal
6 | Storage at central level | [10 empty] | 46500
6.1 | Assess the warehouse infrastructure and evaluate/adapt the existing SOPs for storage | X |  |  | X |  |  |  |  | NDRA & PMU |  | 0
6.2 | Follow up activities in infrastructure & SoPs | X | X |  | X | X |  |  |  | PMU | Medical stores
6.2.1 | Procure data loggers for storage & distribution | X | [7 empty] | PMU |  | 24000 | Procure 60 for central stores, 140 for district stores and 100 for key ART sites | USD24,000 (USD 16k for UNDP & USD8k for MoH)
6.2.4 | Adapt infrastructure (fill details) | X | X |  |  | X |  |  |  | PMU |  | 20000 | 50 % UNDP & Medical stores | Central warehouse racking + provision for receiving software at medical stores
6.3 | Regular inspection visits (once in 6 months) | X |  | X |  | X |  | X |  | NDRA & PMU | QA task force | 2500
7 | Storage at peripheral levels | [10 empty] | 27000
7.1 | Assessment of the warehouse infrastructure and evaluate the existing SOPs for storage. | X | X | X | [5 empty] | NDRA & PMU
7.1.1 | Prepare an assessment approach, plan, calendar & budget. | X | [7 empty] | PMU & MoH |  | 5000 | R7 TB | 2 Day workshop
7.1.2 | Collect available data on storage assessments. | X | [7 empty] | UNDP | MoH and partners | 2000 | R7 TB
7.1.3 | Collect additional information on storage |  | X | X | [5 empty] | PMU | QA task force | 20000 | R7 TB R8 HIV
8 | Distribution | [10 empty] | 3000
8.1 | Assess transport vehicles, rosters & conditions | [8 empty] | PMU | QA task force | 500 | R10 HIV
8.1.1 | Assess central stores ransport vehicles, rosters & conditions for distribution to districts | X | [7 empty] | PMU | Medical stores | 500 | R10 HIV
8.1.3 | Assess transport vehicles, rosters & conditions for distribution from districts to HF by collectingreports and data and completing progressively | TBD | [7 empty] | QA task force | PMU | 2000 | R10 HIV
9 | Pharmaceutical waste management | [10 empty] | 10000
9.1 | Preparation of a waste management plan for GF supplies and other essential drugs |  | X | [6 empty] | PMUs &Central stores | NDRA + QA task force | 10000 | R7 TB R8 HIV
9.1.1. | Develop/adapt SOP for waste collection and disposal at central level | X | X | [6 empty] | Central Stores and NDRA | PMU + QA task force
9.1.2 | Prepare a detailed action plan and budget to deal with existing back log | X | X | [6 empty] | Central Stores and NDRA | PMU + QA task force
9.1.3 | Agree on a long term option for disposal/incineration of drug waste |  | X | [6 empty] | Central Stores and NDRA | PMU + QA task force
9.1.4 | Identify causes of expiry, presence of obsolete and damaged drugs and lab supplies as well as actions to avoid the same in the future | X | X |  |  | X |  |  |  | QA task force
10 | Pharmacovigilance | [10 empty] | 47000
10.1 | Discuss on the Pharmacovigilance Plan prepared by NDRA and identify priority actions and a "pilot" program, for specific areas, diseases or products. | X | X | [6 empty] | PMUs | NDRA | 2000 | R7 TB R8 HIV
10.2 | Conduct a pilot program in 20 Districts and/or sentinel sites within these districts. |  | X | X | X | X |  |  |  | NDRA | PMU + QA task force | 45000 | R10 HIV
11 | Rational drug use (RDU) | [10 empty] | 30000
11.1 | Assess the use of O.I. drugs for HIV patients and identify actions to improve rational use. | X | X | [6 empty] | PMUs | MoH | 10000 | R7 TB R8 HIV | Public Health & Clinical Care Directorate
11.2 | Implement progressively actions identified above |  |  | X | X | X | X |  |  | QA task force | PMU/MoH | 20000 | R8 HIV
12 | Capacity development (CD) | [10 empty] | 124500
12.1 | Support Medical Stores activities for CD of PSM at district level
12.1.1 | Assist in the equipment of the training facilities with furniture and IT equipment | X | X | [6 empty] | UNDP | Medical Stores | 77000 | R8 HIV | Already in PSM plan
12,1,2 | Indentify areas for collaboration for CD improved QA in PSM of GF commodities between partners |  | X | X | [5 empty] | PMU | Medical Stores | 0
12.2 | Assist in building a QA team/taskforce | [8 empty] | PMU | QA task force | 47500
12.2.1 | Promote the establishment of the task force and organise regular meetings | X |  | X |  | X |  | X |  | QA task force | PMU | 7500 | R7 TB R8 and R10 HIV
12.2.2 | Organise a QA training on subjects as preparation of sampling plans, sampling of pharma, principles of pharmacovigilance, inspection of storage facilities.. |  | X | [6 empty] | QA task force | PMU & PSO | 20000 | R7 TB R8 HIV
12.3 | Participate in PSO annual seminar and propose presentations/training sessions (20 national participants 5 days in-country) |  |  | X |  |  | X |  |  | QA task force | PMU & PSO | 20000 | CD
13 | Monitoring & Evaluation | [10 empty] | 10000
13.1 | As per 12.2.1 + ensure budgets are secured in the GF grants and advocate for funding for QA activities in budgets of other donors | X |  | X |  | X |  | X |  | PMU | QA task force | 6000 | R8 and 10 HIV
13.2 | Monitor progress of the QAP and report to the QA task force | X |  | X |  | X |  | X |  | PMU |  | 0
13.3 | Update the QA plan |  |  |  | X |  |  |  | X | PMU | QA task force | 4000 | R8 and 10 HIV
[11 empty] | Total US $ | 304000
Note on K3: guy.rino.meyers: primary responsible
Note on L3: guy.rino.meyers: partners to sahre responsibility
Note on N3: guy.rino.meyers: insert who is contributing and from which grant
Note on O3: guy.rino.meyers: add additional clarifications

## Annex 9 B perf frame
Annex 9 B Country action plan 2 years performance framework
Performance framework
N° | Activities | Q1 | Q2 | Q3 | Q4 | Q5 | Q6 | Q7 | Q8 | Objective 1 | Objective 2 | Indicators | R1 | R2 | Budget | Contribution | Observation
1 | Supply sourcing | [8 empty] | Information on registered suppliers updated and available to PMU and partners | All GF supplies are registered at arrival or waiver is obtained |  |  |  | 0
1.1 | Prepare a listing of the registered suppliers for all pharmaceuticals included in the procurement plans for GF grants | [10 empty] | List of registered suppliers available | PMU UNDP | NDRA | 0 | bar: Q1; Q5
1.2 | Regular updating of this list of registered suppliers | [10 empty] | List of registered suppliers up to date | PMU | NDRA | 0 | bar: Q2; Q6
1.3 | Prepare issuing of temporary waivers by NDRA | [10 empty] | SOP ready and all waivers requested obtained | PMU | NDRA | 0 | bar: Q1; Q6
1.4 | Prepare a briefing for suppliers of non registered drugs on the fast track procedures and costs for registration of drugs | [10 empty] | Briefing note | PMU | NDRA | 0 | bar: Q1
2 | Transport requirements | [8 empty] | Tender/Procurement documents include requirements for freight | Freight conditions correct for all GF suppliers |  |  |  | 1000
2.1 | Adaptation of tender/procurement documents in relation to QA related freight requirements | [10 empty] | List of requirements and PO documentation available | PMU |  | 0 | bar: Q1
2.2 | Revision & Update on the freight requirements | [10 empty] | List of requirements and PO documentation revised | PMU |  | 0 | bar: Q3; Q6
2.3 | Analyse overall data (refer 4.3) on transport conditions and proceed with relevant follow up actions | [10 empty] | Analysis of real freight conditions done and documented | QA task force |  | 1000 | 80 % UNDP. 20 % CHAZ | bar: Q3; Q7
3 | Transit | [8 empty] | Transit storage and transport conditions without negative influence on the quality of health supplies |  |  |  |  | 0
3.1 | Evaluation of the storage conditions at the port of entry (warehouses at the airport). | [10 empty] | Evaluation reports available | NDRA | PMU | 0 | bar: Q1; Q6
4 | Receiving | [8 empty] | Supplies received according to SOP and completely documented |  |  |  |  | 1500
4.1 | Reception of the consignments according to the SoP | [11 empty] | MSL & CHAZ | UNDP, MoH & CHAZ Procurement Teams | 0 | bar: Q2 to Q8
4.2 | Preparation of the receiving report | [10 empty] | Reports available at MSL/Chaz | MSL & CHAZ | UNDP, MoH & CHAZ Procurement Teams | 0 | bar: Q2 to Q8
4.3 | Verification of the data loggers & individual follow up action. | [10 empty] | Data logger data sunnarized | MSL & CHAZ | UNDP, MoH & CHAZ Procurement Teams | 0 | bar: Q2 to Q8
4.4 | Reporting on any discrepancies on the recieved consignments within 24 hours | [10 empty] | Report available | MSL & CHAZ | UNDP, MoH & CHAZ Procurement Teams | 0 | bar: Q2 to Q8
4.5 | Sampling of consignments at receiving | [10 empty] | Progress sheet from the annual sampling plan | MSL & CHAZ | NDRA | 0 | bar: Q2 to Q8
4.6 | Evaluation of the results of receiving: volume and specs discrepencies, noted and confirmed QC problem. | [10 empty] | Report available | QA task force |  | 500 | bar: Q5
4.7 | Adaptation of receiving SOP and information provided to relevant sections of PMU and partners | [10 empty] | SOP updated | QA task force | MSL & CHAZ | 1000 | bar: Q5 to Q6
5 | Quality control for pharmaceuticals & non-pharmaceuticals | [8 empty] | QC done for a representative sample of supplies | QC results used to release supplies or corrective measures |  |  |  | 3000
5.1 | Prepare an annual sampling plan | [10 empty] | Annual sampling plans available | PMU | NDRA & PSO | 3000 | R4 | bar: Q2; Q5
6 | Storage at central level | [8 empty] | Quality of storage at central level guaranteed and documented according GSP |  |  |  |  | 29000
6.1 | Assess the warehouse infrastructure and evaluate/adapt the existing SOPs for storage | [10 empty] | Warehouse assessment report available | NDRA & PMU |  | 0 | bar: Q1; Q4
6.2 | Follow up activities in infrastructure & SoPs | [11 empty] | PMU | CHAZ & MSL | bar: Q1 to Q2; Q4 to Q5
6.2.1 | Procure data loggers for storage & distribution | [10 empty] | Data loggers available in Zambia | PMU |  | 25000 | Procure 10 for CHAZ & 50 for MSL | USD21,000 (USD8k for UNDP & USD4k for CHAZ) | bar: Q1
6.2.4 | Adapt infrastructure (fill details) | [10 empty] | Warehouse racked | PMU | CHAZ & MSL | 4000 | 80 % UNDP. 20 % CHAZ | bar: Q1 to Q2; Q5
6.3 | Regular inspection visits (once in 6 months) | [10 empty] | Inspection reports | MSL, CHAZ & NDRA | PMU | 0 | bar: Q1; Q3; Q5; Q7
7 | Storage at peripheral levels | [8 empty] | Quality of storage at peripheral level documented and progressively monitored |  |  |  |  | 27000
7.1 | Assessment of the warehouse infrastructure and evaluate the existing SOPs for storage. | [10 empty] | Data available on peripheral storage compiled and documented | NDRA & PMU | bar: Q1 to Q3
7.1.1 | Prepare an assessment approach, plan, calendar & budget. | [11 empty] | PMU & MoH |  | 5000 | R4 | 2 Day workshop | bar: Q1
7.1.2 | Collect available data on storage assessments. | [11 empty] | UNDP | MSL, WB, JSI & CHAZ | 2000 | R4 | bar: Q1
7.1.3 | Collect additional information on storage | [11 empty] | PMU | QA task force | 20000 | R7 R8 | bar: Q2 to Q3
8 | Distribution | [8 empty] | Distribution from central to district level according to GDP guidelines | Distribution from district level to HF documented |  |  |  | 0
8.1 | Assess transport vehicles, rosters & conditions | [11 empty] | PMU | QA task force | 0
8.1.1 | Assess central stores ransport vehicles, rosters & conditions for distribution to districts | [10 empty] | Assessment report available | PMU | MSL & CHAZ | 0 | bar: Q1
8.1.3 | Assess transport vehicles, rosters & conditions for distribution from districts to HF by collectingreports and data and completing progressively | Q1: TBD |  |  | Assessment report available | PMU | MSL & CHAZ | 0
9 | Pharmaceutical waste management | [8 empty] | Pharmaceutical waste correctly managed according to SOP | All existing pharmaceutical waste progressively correctly disposed |  |  |  | 10000
9.1 | Preparation of a waste management plan for GF supplies and other essential drugs | [10 empty] | Waste management plan agreed on | PMUs & MSL | NDRA + QA task force | 10000 | R4 R8 | bar: Q2
9.1.1. | Develop/adapt SOP for waste collection and disposal at central level | [11 empty] | MSL, CHAZ, NDRA | PMU + QA task force | bar: Q1 to Q2
9.1.2 | Prepare a detailed action plan and budget to deal with existing back log | [11 empty] | MSL, CHAZ, NDRA | PMU + QA task force | bar: Q1 to Q2
9.1.3 | Agree on a long term option for disposal/incineration of drug waste | [11 empty] | MSL, CHAZ, NDRA | PMU + QA task force | bar: Q2
9.1.4 | Identify causes of expiry, presence of obsolete and damaged drugs and lab supplies as well as actions to avoid the same in the future | [11 empty] | QA task force | bar: Q1 to Q2; Q5
10 | Pharmacovigilance (PV) | [8 empty] | Pharmacovigilance pilot program described, implemented and evaluated | Pharmacovigilance program roll out started |  |  |  | #REF!
10.1 | Discuss on the Pharmacovigilance Plan prepared by NDRA and identify priority actions and a "pilot" program, for specific areas, diseases or products. | [10 empty] | PV pilot program agreed on | PMUs | NDRA | 2000 | R4 R8 | bar: Q1 to Q2
10.2 | Conduct a pilot program in 20 Districts and/or sentinel sites within these districts. | [10 empty] | PV pilot program implemented and monitored | NDRA | PMU + QA task force | #REF! | R10 HIV | bar: Q2 to Q5
11 | Rational drug use (RDU) | [8 empty] | Specific problems on RDU addressed | NF updated and dissiminated |  |  |  | #REF!
11.1 | Assess the use of O.I. drugs for HIV patients and identify actions to improve rational use. | [10 empty] | Assessment report on OI | PMUs | NDRA | 10000 | R4 R8 HIV | Public Health & Clinical Care Directorate | bar: Q1 to Q2
11.2 | Implement progressively actions identified above | [10 empty] | Results documented | QA task force | PMU/NACP | 20000 | R8 HIV | bar: Q3 to Q6
12 | Capacity development (CD) | [8 empty] | QA task force formed, team build and trained | Capacity build in a number of QA PSM areas |  |  |  | 124500
12.1 | Support Medical Stores activities for CD of PSM at district level | [10 empty] | Medical Stores capacity building unit operational and used
12.1.1 | Assist in the equipment of the training facilities with furniture and IT equipment | [10 empty] | Supplies provided in time | UNDP | MSL | 77000 | R8 HIV | Already in PSM plan | bar: Q1 to Q2
12,1,2 | Indentify areas for collaboration for CD improved QA in PSM of GF commodities between partners | [10 empty] | CD unit used beyond Medical Stores direct needs only. | PMU | MSL | 0 | bar: Q2 to Q3
12.2 | Assist in building a QA team/taskforce | [10 empty] | QA task force motivated and trained | PMU | QA task force | 0
12.2.1 | Promote the establishment of the task force and organise regular meetings | [10 empty] | Meeting minutes | QA task force | PMU | 7500 | R4 R8 R10 | bar: Q1; Q3; Q5; Q7
12.2.2 | Organise a QA training on subjects as preparation of sampling plans, sampling of pharma, principles of pharmacovigilance, inspection of storage facilities.. | [10 empty] | QA training summary | QA task force | PMU & PSO | 20000 | R4 R8 | bar: Q2
12.3 | Participate in PSO annual seminar and propose presentations/training sessions (20 national participants 5 days in-country) | [10 empty] | Number of country participants in PSO training seminar | QA task force | PMU & PSO | 20000 | R8 | bar: Q3; Q6
13 | Monitoring & Evaluation | [8 empty] | QA plan implemented and documented | QA plan owned by the QA task force |  |  |  | 10000
13.1 | As per 12.2.1 + ensure budgets are secured in the GF grants and advocate for funding for QA activities in budgets of other donors | [10 empty] | QA funds mobilised beyond GF grant funding | PMU | QA task force | 6000 | R8 and 10 HIV | bar: Q1; Q3; Q5; Q7
13.2 | Monitor progress of the QAP and report to the QA task force | [10 empty] | Regular monitoring reports available | PMU |  | 0 | bar: Q1; Q3; Q5; Q7
13.3 | Update the QA plan | [10 empty] | QA plan updated each year | PMU | QA task force | 4000 | R8 and 10 HIV | bar: Q4; Q8
[14 empty] | Total US $ | #REF!

## Ann9 C Budget Execution
| Annex 9 Country action plan 2 years | [18 empty] | Date:
Details budget and budget monitoring | [12 empty] | * |  | * |  | Funded | Mobilize | Total | Executed
N° | Activities | Q1 | Q2 | Q3 | Q4 | Q5 | Q6 | Q7 | Q8 | R1 | R2 | Budget | G1 | Amount1 | G2 | Amount2 | Budget | Budget | Budget | Budget | Budget
1 | Supply sourcing | [10 empty] | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0
1.1 | Prepare a listing of the registered suppliers for all pharmaceuticals included in the procurement plans for GF grants | X |  |  |  | X |  |  |  | PMU UNDP | NDRA | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0
1.2 | Regular updating of this list of registered suppliers |  | X |  |  |  | X |  |  | PMU | NDRA | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0
1.3 | Prepare issuing of temporary waivers by NDRA | X |  |  |  |  | X |  |  | PMU | NDRA | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0
1.4 | Prepare a briefing for suppliers of non registered drugs on the fast track procedures and costs for registration of drugs | X | [7 empty] | PMU | NDRA | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | G ref | Amount plan
2 | Transport requirements | [10 empty] | 1000 |  |  |  |  | 800 | 200 | 1000 | 0 | 1000 | 1 | 28800
2.1 | Adaptation of tender/procurement documents in relation to QA related freight requirements | X | [7 empty] | PMU |  | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 2 | 18500
2.2 | Revision & Update on the freight requirements |  |  | X |  |  | X |  |  | PMU |  | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 3 | 155700
2.3 | Analyse overall data (refer 4.3) on transport conditions and proceed with relevant follow up actions |  |  | X |  |  |  | X |  | QA task force |  | 1000 | 1 | 800 | 6 | 200 | 800 | 200 | 1000 | 0 | 1000 | 4 | 53000
3 | Transit | [10 empty] | 500 |  |  |  |  | 500 | 0 | 500 | 0 | 500 | 5 | 43800
3.1 | Evaluation of the storage conditions at the port of entry (warehouses at the airport). | X |  |  |  |  | X |  |  | NDRA | PMU | 500 | 2 | 500 |  |  | 500 | 0 | 500 | 0 | 500 | 6 | 4200
4 | Receiving | [10 empty] | 1500 |  |  |  |  | 1500 | 0 | 1500 | 0 | 1500 | Total | 304000
4.1 | Reception of the consignments according to the SoP |  | X | X | X | X | X | X | X | MSL & CHAZ | UNDP, MoH & CHAZ Procurement Teams | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0
4.2 | Preparation of the receiving report |  | X | X | X | X | X | X | X | MSL & CHAZ | UNDP, MoH & CHAZ Procurement Teams | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0
4.3 | Verification of the data loggers & individual follow up action. |  | X | X | X | X | X | X | X | MSL & CHAZ | UNDP, MoH & CHAZ Procurement Teams | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0
4.4 | Reporting on any discrepancies on the recieved consignments within 24hours |  | X | X | X | X | X | X | X | MSL & CHAZ | UNDP, MoH & CHAZ Procurement Teams | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0
4.5 | Sampling of consignments at receiving |  | X | X | X | X | X | X | X | MSL & CHAZ | NDRA | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0
4.6 | Evaluation of the results of receiving: volume and specs discrepencies, noted and confirmed QC problem. |  |  |  |  | X |  |  |  | QA task force |  | 500 | 1 | 500 |  |  | 500 | 0 | 500 | 0 | 500
4.7 | Adaptation of receiving SOP and information provided to relevant sections of PMU and partners |  |  |  |  | X | X |  |  | QA task force | MSL & CHAZ | 1000 | 1 | 1000 |  |  | 1000 | 0 | 1000 | 0 | 1000
5 | Quality control for pharmaceuticals & non-pharmaceuticals | [10 empty] | 3000 |  |  |  |  | 3000 | 0 | 3000 | 0 | 3000
5.1 | Prepare an annual sampling plan |  | X |  |  | X |  |  |  | PMU | NDRA & PSO | 3000 | 2 | 2000 | 2 | 1000 | 3000 | 0 | 3000 | 0 | 3000
6 | Storage at central level | [10 empty] | 46500 |  |  |  |  | 42500 | 4000 | 46500 | 0 | 46500
6.1 | Assess the warehouse infrastructure and evaluate/adapt the existing SOPs for storage | X |  |  | X |  |  |  |  | NDRA & PMU |  | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0
6.2 | Follow up activities in infrastructure & SoPs | X | X |  | X | X |  |  |  | PMU | CHAZ & MSL
6.2.1 | Procure data loggers for storage & distribution | X | [7 empty] | PMU |  | 24000 | 3 | 20000 | 6 | 4000 | 20000 | 4000 | 24000 | 0 | 24000
6.2.4 | Adapt infrastructure (fill details) | X | X |  |  | X |  |  |  | PMU | CHAZ & MSL | 20000 | 5 | 20000 |  |  | 20000 | 0 | 20000 | 0 | 20000
6.3 | Regular inspection visits (once in 6 months) | X |  | X |  | X |  | X |  | MSL, CHAZ & NDRA | PMU | 2500 | 3 | 1700 | 5 | 800 | 2500 | 0 | 2500 | 0 | 2500
7 | Storage at peripheral levels | [10 empty] | 27000 |  |  |  |  | 27000 | 0 | 27000 | 0 | 27000 | QC testing
7.1 | Assessment of the warehouse infrastructure and evaluate the existing SOPs for storage. | X | X | X | [5 empty] | NDRA & PMU | [11 empty] | 20000 | R7 TB
7.1.1 | Prepare an assessment approach, plan, calendar & budget. | X | [7 empty] | PMU & MoH |  | 5000 | 1 | 5000 |  |  | 5000 | 0 | 5000 | 0 | 5000 | 15000 | R8 Mal
7.1.2 | Collect available data on storage assessments. | X | [7 empty] | UNDP | MSL, WB, JSI & CHAZ | 2000 | 1 | 2000 |  |  | 2000 | 0 | 2000 | 0 | 2000 | 4000 | R8 HIV
7.1.3 | Collect additional information on storage |  | X | X | [5 empty] | PMU | QA task force | 20000 | 1 | 5000 | 2 | 15000 | 20000 | 0 | 20000 | 0 | 20000 | 11000 | R10 HIV
8 | Distribution | [10 empty] | 3000 |  |  |  |  | 3000 | 0 | 3000 | 0 | 3000 | 50000 | Total
8.1 | Assess transport vehicles, rosters & conditions | [8 empty] | PMU | QA task force | 500 | 5 | 500 |  |  | 500 | 0 | 500 | 0 | 500
8.1.1 | Assess MSL transport vehicles, rosters & conditions for distribution from MSL to districts | [8 empty] | PMU | MSL & CHAZ | 500 | 5 | 500 |  |  | 500 | 0 | 500 | 0 | 500
8.1.2 | Assess transport vehicles, rosters & conditions for distribution from CHAZ to HF | [8 empty] | PMU | MSL & CHAZ | 2000 | 5 | 2000 |  |  | 2000 | 0 | 2000 | 0 | 2000
9 | Pharmaceutical waste management | [10 empty] | 10000 |  |  |  |  | 10000 | 0 | 10000 | 0 | 10000
9.1 | Preparation of a waste management plan for GF supplies and other essential drugs |  | X | [6 empty] | PMUs & MSL | NDRA + QA task force | 10000 |  |  |  |  | 10000 | 0 | 10000 | 0 | 10000
9.1.1. | Develop/adapt SOP for waste collection and disposal at central level | X | X | [6 empty] | MSL, CHAZ, NDRA | PMU + QA task force |  | 1 | 2500
9.1.2 | Prepare a detailed action plan and budget to deal with existing back log | X | X | [6 empty] | MSL, CHAZ, NDRA | PMU + QA task force |  | 3 | 2500
9.1.3 | Agree on a long term option for disposal/incineration of drug waste |  | X | [6 empty] | MSL, CHAZ, NDRA | PMU + QA task force |  | 3 | 2500
9.1.4 | Identify causes of expiry, presence of obsolete and damaged drugs and lab supplies as well as actions to avoid the same in the future | X | X |  |  | X |  |  |  | QA task force |  |  | 3 | 2500
10 | Pharmacovigilance (PV) | [10 empty] | 47000 |  |  |  |  | 47000 | 0 | 47000 | 0 | 47000
10.1 | Discuss on the Pharmacovigilance Plan prepared by NDRA and identify priority actions and a "pilot" program, for specific areas, diseases or products. | X | X | [6 empty] | PMUs | NDRA | 2000 | 1 | 500 | 3 | 1500 | 2000 | 0 | 2000 | 0 | 2000
10.2 | Conduct a pilot program in 20 Districts and/or sentinel sites within these districts. |  | X | X | X | X |  |  |  | NDRA | PMU + QA task force | 45000 | 4 | 45000 |  |  | 45000 | 0 | 45000 | 0 | 45000
11 | Rational drug use (RDU) | [10 empty] | 30000 |  |  |  |  | 30000 | 0 | 30000 | 0 | 30000
11.1 | Assess the use of O.I. drugs for HIV patients and identify actions to improve rational use. | X | X | [6 empty] | PMUs | NDRA | 10000 | 1 | 5000 | 3 | 5000 | 10000 | 0 | 10000 | 0 | 10000
11.2 | Implement progressively actions identified above |  |  | X | X | X | X |  |  | QA task force | PMU/NACP | 20000 | 3 | 20000 |  |  | 20000 | 0 | 20000 | 0 | 20000
12 | Capacity development (CD) | [10 empty] | 124500 |  | 103500 |  | 21000 | 124500 | 0 | 124500 | 0 | 124500
12.1 | Support Medical Stores activities for CD of PSM at district level
12.1.1 | Assist in the equipment of the training facilities with furniture and IT equipment | X | X | [6 empty] | UNDP | MSL | 77000 | 3 | 77000 |  |  | 77000 | 0 | 77000 | 0 | 77000
12,1,2 | Indentify areas for collaboration for CD improved QA in PSM of GF commodities between partners |  | X | X | [5 empty] | PMU | MSL | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0
12.2 | Assist in building a QA team/taskforce | [8 empty] | PMU | QA task force | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 47500
12.2.1 | Promote the establishment of the task force and organise regular meetings | X |  | X |  | X |  | X | X | QA task force | PMU | 7500 | 1 | 1500 | 3+4 | 6000 | 7500 | 0 | 7500 | 0 | 7500
12.2.2 | Organise a QA training on subjects as preparation of sampling plans, sampling of pharma, principles of pharmacovigilance, inspection of storage facilities.. |  | X | [6 empty] | QA task force | PMU & PSO | 20000 | 1 | 5000 | 3 | 15000 | 20000 | 0 | 20000 | 0 | 20000
12.3 | Participate in PSO annual seminar and propose presentations/training sessions (20 national participants 5 days in-country) |  |  | X |  |  | X |  |  | QA task force | PMU & PSO | 20000 | 5 | 20000 |  |  | 20000 | 0 | 20000 | 0 | 20000
13 | Monitoring & Evaluation | [10 empty] | 10000 |  |  |  |  | 10000 | 0 | 10000 | 0 | 10000
13.1 | As per 12.2.1 + ensure budgets are secured in the GF grants and advocate for funding for QA activities in budgets of other donors |  | X |  | X |  | X |  | X | PMU | QA task force | 6000 | 3 | 3000 | 4 | 3000 | 6000 | 0 | 6000 | 0 | 6000
13.2 | Monitor progress of the QAP and report to the QA task force |  | X |  | X |  | X |  | X | PMU |  | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0
13.3 | Update the QA plan |  |  | X |  |  |  | X |  | PMU | QA task force | 4000 | 3 | 2000 | 4 | 2000 | 4000 | 0 | 4000 | 0 | 4000
[11 empty] | Total US $ | 304000 |  |  |  |  | 299800 | 4200 | 304000 | 0 | 304000
List of grants / sources of funding
1 | R7 TB | [9 empty] | R10 HIV
2 | R8 MAL | [9 empty] | R7 TB
3 | R8 HIV | [9 empty] | R7 Mal
4 | R10 HIV
5 | Capacity development budget of different grants | [9 empty] | R8 HIV
6 | To mobilize
R 8-10 Chaz
Note on N3: guy.rino.meyers: Grant contribution 1. see grant ref table
Note on P3: guy.rino.meyers: Grant contribution 2
Note on X31: guy.rino.meyers: Costs to be included inn the plan in relation to the volume of procurement per grant
Note on N59: Guy.Rino.Meyers: 17 000 from CD budget clear 2 and replace

## Annex 10 Budget summary
Annex 9 Summary Budget' Country action plan 2 years
Budget summary
N° | Activities | 2012 | 2013 | Budget | Contributions | Observations
1 | Supply sourcing |  |  | 0
2 | Transport requirements | 500 | 500 | 1000
3 | Transit | 500 |  | 500
4 | Receiving | 1500 |  | 1500
5 | Quality control for pharmaceuticals & non-pharmaceuticals | 3000 |  | 3000
6 | Storage at central level | 40000 | 6500 | 46500
7 | Storage at peripheral levels | 20000 | 7000 | 27000
8 | Distribution | 3000 |  | 3000
9 | Pharmaceutical waste management | 8000 | 2000 | 10000
10 | Pharmacovigilance | 40000 | 7000 | 47000
11 | Rational drug use (RDU) | 25000 | 5000 | 30000
12 | Capacity development | 85000 | 39500 | 124500
13 | Monitoring & Evaluation | 5000 | 5000 | 10000
|  | 231500 | 72500 | 304000