## Annex 9 B perf frame
Annex 9 B Zambia action plan 2012 - 2013 performance framework
Performance framework
N° | Activities | Q0 | Q1 | Q2 | Q3 | Q4 | Q5 | Q6 | Q7 | Q8 | Objective 1 | Objective 2 | Indicators |  | R1 | R2 | Budget | Contribution | Observation
1 | Supply sourcing | [9 empty] | Information on registered suppliers updated and available to PMU and partners | All GF supplies are registered at arrival or waiver is obtained |  |  |  |  | 0
1.1 | Prepare a listing of the registered suppliers for all pharmaceuticals included in the procurement plans for GF grants | [11 empty] | List of registered suppliers available |  | PMU UNDP | PRA | 0 | bar: Q0 to Q1; Q4
1.2 | Regular updating of this list of registered suppliers | [11 empty] | List of registered suppliers up to date |  | PMU | PRA | 0 | bar: Q1; Q5
1.3 | Prepare issuing of temporary waivers by PRA | [11 empty] | SOP ready and all waivers requested obtained |  | PMU | PRA | 0 | bar: Q0 to Q1; Q5
1.4 | Prepare a briefing for suppliers of non registered drugs on the fast track procedures and costs for registration of drugs | [11 empty] | Briefing note |  | PMU | PRA | 0 | bar: Q0 to Q1
2 | Transport requirements | [9 empty] | Tender/Procurement documents include requirements for freight | Freight conditions correct for all GF suppliers |  |  |  |  | 1000
2.1 | Adaptation of tender/procurement documents in relation to QA related freight requirements | [11 empty] | List of requirements and PO documentation available |  | PMU |  | 0 | bar: Q0 to Q1
2.2 | Revision & Update on the freight requirements | [11 empty] | List of requirements and PO documentation revised |  | PMU |  | 0 | bar: Q2; Q5
2.3 | Analyse overall data (refer 4.3) on transport conditions and proceed with relevant follow up actions | [11 empty] | Analysis of real freight conditions done and documented |  | QA task force |  | 1000 | 80 % UNDP. 20 % CHAZ | bar: Q2; Q6
3 | Transit | [9 empty] | Transit storage and transport conditions without negative influence on the quality of health supplies | [5 empty] | 1500
3.1 | Evaluation of the storage conditions at the port of entry (warehouses at the airport). | [11 empty] | Evaluation reports available |  | PRA | PMU | 0 | bar: Q0 to Q1; Q5
3.2 | SOP for clearing/pre-clearing of shipments into the country (including obtaining of permits from the PRA) | [11 empty] | SOP available |  | PMU | PRA | 0 | bar: Q0 to Q1
3.3 | Evaluate and compare the results of the pre-clearing including transit times & adapt SoP. | [11 empty] | Monitoring reports for temp and humidity during transit storage |  | PMU | PRA | 500 | bar: Q4
3.4 | Evaluation of transport conditions to the respective warehouses.From the second time using also data from the dataloggers and follow up actions | [11 empty] | Monitoring reports for temp and humidity during transit transport |  | PMU |  | 1000 |  | Need for evaluation form ... | bar: Q0 to Q1; Q4 to Q5
4 | Receiving | [9 empty] | Supplies received according to SOP and completely documented | [5 empty] | 1500
4.1 | Reception of the consignments according to the SoP | [13 empty] | MSL & CHAZ | UNDP, MoH & CHAZ Procurement Teams | 0 | bar: Q1 to Q8
4.2 | Preparation of the receiving report | [11 empty] | Reports available at MSL/Chaz |  | MSL & CHAZ | UNDP, MoH & CHAZ Procurement Teams | 0 | bar: Q1 to Q8
4.3 | Verification of the data loggers & individual follow up action. | [11 empty] | Data logger data sunnarized |  | MSL & CHAZ | UNDP, MoH & CHAZ Procurement Teams | 0 | bar: Q1 to Q8
4.4 | Reporting on any discrepancies on the recieved consignments within 24hours | [11 empty] | Report available |  | MSL & CHAZ | UNDP, MoH & CHAZ Procurement Teams | 0 | bar: Q1 to Q8
4.5 | Sampling of consignments at receiving | [11 empty] | Progress sheet from the annual sampling plan |  | MSL & CHAZ | PRA | 0 | bar: Q1 to Q8
4.6 | Evaluation of the results of receiving: volume and specs discrepencies, noted and confirmed QC problem. | [11 empty] | Report available |  | QA task force |  | 500 | bar: Q4
4.7 | Adaptation of receiving SOP and information provided to relevant sections of PMU and partners | [11 empty] | SOP updated |  | QA task force | MSL & CHAZ | 1000 | bar: Q4 to Q5
5 | Quality control for pharmaceuticals & non-pharmaceuticals | [9 empty] | QC done for a representative sample of supplies | QC results used to release supplies or corrective measures |  |  |  |  | 148000
5.1 | Prepare an annual sampling plan | [11 empty] | Annual sampling plans available |  | PMU | PRA & PSO | 3000 | R4 | bar: Q0 to Q1; Q4
5.2 | Selection of the laboratories for QC testing (* refer also to 12.5) | [11 empty] | Laboratories selected |  | PMU | PRA & PSO | 0 | bar: Q0 to Q1; Q3
5.3 | Evaluation of performance of the QC labs and provide recommendations for follow up | [11 empty] | Annual evaluation reports available |  | PMU |  | 2000 | R8 | bar: Q3; Q7
5.4 | Sampling | [11 empty] | Samples tested and reports available |  | MSL & CHAZ | PMU,PRA | 0 | bar: Q1 to Q8
5.4.1 | Sampling of consignments at receiving | [11 empty] | Progress sheet from the annual sampling plan |  | MSL & CHAZ | PMU,PRA | 0 | bar: Q1 to Q8
5.4.2 | Sampling of products in the field according to sampling plan | [11 empty] | Progress sheet from the annual sampling plan |  | MSL & CHAZ | PMU,PRA | 0 | bar: Q1 to Q8
5.4.3 | Sampling of products irelated to additionally identified risks | [11 empty] | Progress sheet from the annual sampling plan |  | MSL & CHAZ | PMU,PRA | 0 | bar: Q1 to Q8
5.5 | Completion of the sample collection forms | [13 empty] | PMU | Receiving committees | 0 | bar: Q1 to Q8
5.6 | Obtain export license from PRA for the samples. | [11 empty] | List of export licences obtained |  | PMU | PRA | 0 | bar: Q1 to Q8
5.7 | Forwarding of samples to relevant laboratories and have them tested | [11 empty] | Samples tested and reports available |  | PMU |  | 140000 | 80 % UNDP. 20 % CHAZ | 70,000 per year specifric per grant | bar: Q1 to Q8
5.8 | Monitoring the laboratory response time | [11 empty] | Annual report on QC testing |  | PMU |  | 0 | bar: Q1 to Q8
5.9 | Interpretation of the results from the laboratories | [11 empty] | Negative results discussed and documented |  | MSL, CHAZ & PRA | PMU | 0 | bar: Q1 to Q8
5.10. | Follow up actions | [11 empty] | Products out of specs quarantined and disposed, measures with regards to suppliers taken |  | PRA | QA task force | 3000 | 80 % UNDP. 20 % CHAZ | R7, R8 and R 10 | bar: Q1 to Q8
6 | Storage at central level | [9 empty] | Quality of storage at central level guaranteed and documented according GSP | [5 empty] | 49500
6.1 | Assess the warehouse infrastructure and evaluate/adapt the existing SOPs for storage | [11 empty] | Warehouse assessment report available |  | PRA & PMU |  | 0 | bar: Q1; Q3
6.2 | Follow up activities in infrastructure & SoPs | [13 empty] | PMU | CHAZ & MSL | bar: Q1; Q3 to Q4
6.2.1 | Procure data loggers for storage & distribution | [11 empty] | Data loggers available in Zambia |  | PMU |  | 25000 | Procure 10 for CHAZ & 50 for MSL | USD21,000 (USD8k for UNDP & USD4k for CHAZ) | bar: Q0 to Q1
6.2.2 | Include the use of data loggers in the SOP and monitor the storage conditions on a regular basis and ensure basic training | [13 empty] | PMU | CHAZ & MSL | 4000 | 80 % UNDP. 20 % CHAZ | bar: Q1 to Q8
6.2.3 | Adapt SOP if and where required | [13 empty] | MSL, CHAZ & PRA | PMU | 0 | bar: Q1; Q3
6.2.4 | Adapt infrastructure (for CHAZ: install racking +) | [11 empty] | CHAZ warehouse racked |  | PMU |  | 20000 | 50 % UNDP & CHAZ | CHAZ Central warehouse racking + provision for receiving at MSL | bar: Q1 to Q2; Q4
6.2.5 | Procure a reach truck for MSL central warehouse | [11 empty] | Reach truck operational | bar: Q0 to Q1
6.3 | Regular inspection visits (once in 6 months) | [11 empty] | Inspection reports |  | PRA & PMU | QA task force | 500 | bar: Q1; Q3; Q5; Q7
7 | Storage at peripheral levels | [9 empty] | Quality of storage at peripheral level documented and progressively monitored | [5 empty] | 327000
7.1 | Assessment of the warehouse infrastructure and evaluate the existing SOPs for storage. | [11 empty] | Data available on peripheral storage compiled and documented |  | PRA & PMU | bar: Q1 to Q3
7.1.1 | Prepare an assessment approach, plan, calendar & budget. | [13 empty] | PMU & MoH |  | 5000 | R4 | 2 Day workshop | bar: Q1
7.1.2 | Collect available data on storage assessments. | [13 empty] | UNDP | MSL, WB, JSI & CHAZ | 2000 | R4 | bar: Q1
7.1.3 | Collect additional information on storage | [13 empty] | PMU | QA task force | 20000 | R7 R8 | bar: Q1 to Q2
7.2 | Follow up activities in infrastructure & SoPs | [11 empty] | CD plan for storage at peripheral level described and joint implementation started |  | PMU | CHAZ & MSL | 100000 |  | TBD | bar: Q2 to Q8
7.2.1 | Transfer and install 10 refer containers to district medical stores | [11 empty] | 10 refer containers installed for improved capacity at district stores | bar: Q1 to Q4
7.3 | Procure data loggers for storage & distribution see under 6.2.1 | [11 empty] | Storage facilities provided with data loggers and data monitored |  | PMU | MSL |  |  | 15.000 US $ for this level | bar: Q0 to Q1
7.4 | Regular inspection visits of district and health facility (HF) storage facilities (once in 6 months for districts, once a year for HF) | [11 empty] | Visit reports compiled and summarized |  | PRA & PMU | QA task force | 200000 | 80 % UNDP. 20 % CHAZ | Partial included in regular M&E visits | R11 | bar: Q1 to Q8
8 | Distribution | [9 empty] | Distribution from central to district level according to GDP guidelines | Distribution from district level to HF documented |  |  |  |  | 580000
8.1 | Assess transport vehicles, rosters & conditions | [13 empty] | PMU | QA task force | 0
8.1.1 | Assess MSL transport vehicles, rosters & conditions for distribution from MSL to districts | [11 empty] | Assessment report available |  | PMU | MSL & CHAZ | 0 | bar: Q1
8.1.2 | Assess transport vehicles, rosters & conditions for distribution from CHAZ to HF | [11 empty] | Assessment report available |  | PMU | MSL & CHAZ | 0 | bar: Q1
8.1.3 | Assess transport vehicles, rosters & conditions for distribution from districts to HF by collectingreports and data and completing progressively | Q1: TBD |  |  | Assessment reports available |  | QA task force | PMU
8.2 | Follow up activities on conditions & the infrastructure. | Q1: TBD |  |  |  |  | PMU | MSL & CHAZ |  | refer to 6.2.1 for procurement
8.2.1 | Monitoring of data loggers on the trucks | [11 empty] | Temp and humidity documented for distribution visits |  | MSL & CHAZ | PMU | 0 |  | see 6.2.1 | bar: Q1 to Q8
8.2.2 | Procure transport equipement for MSL to improve capacity and conditions | [11 empty] | MSL transport equipment supplied and operational |  | UNDP | MSL | 530000 | R 8 HIV | In PSM plan | bar: Q0 to Q1
8.2.3 | Adaptation of existing vehicles (insulation, air conditioning ...) at central level at MSL and CHAZ | [11 empty] | Number and % of vehicles correctly equipped |  | PMU | MSL & CHAZ | 50000 | R 8 HIV | In PSM plan | bar: Q1 to Q2
8.2.4 | Review ordering procedures to avoid double ordering from MSL and CHAZ | [9 empty] | MSL/CHAZ | PMU | 0 | bar: Q1
8.3 | Assist in developing district logistics capacity | Q1: TBD |  |  | District distribution CD plan available
9 | Pharmaceutical waste management | [9 empty] | Pharmaceutical waste correctly managed according to SOP | All existing pharmaceutical waste progressively correctly disposed |  |  |  |  | 160000
9.1 | Preparation of a waste management plan for GF supplies and other essential drugs | [11 empty] | Waste management plan agreed on |  | PMUs & MSL | PRA + QA task force | 10000 | R4 R8 | bar: Q1
9.1.1. | Develop/adapt SOP for waste collection and disposal at central level | [13 empty] | MSL, CHAZ, PRA | PMU + QA task force | bar: Q1 to Q2
9.1.2 | Prepare a detailed action plan and budget to deal with existing back log | [13 empty] | MSL, CHAZ, PRA | PMU + QA task force | bar: Q1 to Q2
9.1.3 | Agree on a long term option for disposal/incineration of drug waste | [13 empty] | MSL, CHAZ, PRA | PMU + QA task force | bar: Q1 to Q2
9.1.4 | Identify causes of expiry, presence of obsolete and damaged drugs and lab supplies as well as actions to avoid the same in the future | [13 empty] | QA task force | bar: Q1 to Q2; Q5
9.2 | Waste management and disposal of existing backlog commodities at central | [11 empty] | Backlog at central level removed |  | MSL, CHAZ, PRA | PMU | 30000 | R4 | bar: Q1 to Q3
9.3 | Waste management and disposal of existing backlog commodities at peripheral level. | [11 empty] | Backlog at peripheral central level reduced and progressibly disposed of |  | MSL, CHAZ, PRA | PMU | 30000 | R8 | bar: Q1 to Q4
9.4 | Procure and install an incinerator for pharmaceutical waste at central level | [11 empty] | Incinerator installed |  | PMU | PRA | 60000 | R4 R8 R10 | bar: Q1 to Q2
9.5 | Develop a sustainable model for management of the incinerator/incineration | [11 empty] | Incinerator operational, Sop and costing model approved |  | MSL & CHAZ | PRA | 10000 | R8 | bar: Q1 to Q2
9.6 | Regular disposal of GF expired, obsolete and damaged drugs and lab supplies | [11 empty] | Disposal reports |  | PMU | PRA/Incinerator | 20000 | R8 R10 | over 1,5 years | bar: Q3 to Q8
10 | Pharmacovigilance | [9 empty] | Pharmacovigilance pilot program described, implemented and evaluated | Pharmacovigilance program roll out started |  |  |  |  | 72000
10.1 | Discuss on the Pharmacovigilance Plan prepared by PRA and identify priority actions and a "pilot" program, for specific areas, diseases or products. | [11 empty] | PV pilot program agreed on |  | PMUs | PRA | 2000 | R4 R8 | bar: Q0 to Q1
10.2 | Conduct a pilot program in 20 Districts and/or sentinel sites within these districts. | [11 empty] | PV pilot program implemented and monitored |  | PRA | PMU + QA task force | 55000 | R10 HIV | bar: Q1 to Q4
10.2.1 | Provide the PRA team with IT equipment at central level and improve internet connectivity. | [11 empty] | IT equipment operational |  | PMU | PRA | 11000 | R8 | 2 laptops, scanner copier, internet | bar: Q1
10.2.2 | Subscribe to Vigiflo | [11 empty] | Subscription paid |  | PMU | PRA | 4000 | R 4 R8 R10 | bar: Q1; Q5
10.2.3 | Identification of the districts and sentinel sites. | [11 empty] | Participating sites of the program identified |  | PRA | PMU | 0 | bar: Q1
10.2.4 | Training of health staff of the sentinel sites of the 20 selected districts | [11 empty] | Staff trained |  | PRA | QA task force | 30000 | R8 HIV | 100 staff, two days each 6 sessions, 2 trainers | bar: Q1 to Q2
10.2.5 | Start up, regular meetings of the PV committee, verification and Q reporting | [11 empty] | Monitoring reports |  | PRA | PMU | 10000 | R10 HIV | bar: Q2 to Q5
10.3 | Evaluate the pilot program and explore further potential, actions and budget for roll out. | [11 empty] | Evaluation report pilot |  | QA task force | PMU | 5000 | R10 HIV | bar: Q5
10.4 | Roll out the pharmacovigilance program on a larger scale. | Q1: TBD; Q5: X; Q6: X; Q7: X; Q8: X |  |  | Roll out program document and quarterly reports |  | PRA | PMU + QA task force |  | TBD
10.5 | Identify other specific areas of intervention and activities for GF products and implement. | [11 empty] | Activities implemented and documented |  | PMU | QA task force | 10000 | R11 | bar: Q2; Q5 to Q6
11 | Rational drug use (RDU) | [9 empty] | Specific problems on RDU addressed | NF updated and dissiminated |  |  |  |  | 173000
11.1 | Assess the use of O.I. drugs for HIV patients and identify actions to improve rational use. | [11 empty] | Assessment report on OI |  | PMUs | PRA | 10000 | R4 R8 HIV | Public Health & Clinical Care Directorate | bar: Q1 to Q2
11.2 | Implement progressively actions identified above | [11 empty] | Results documented |  | QA task force | PMU/NACP | 20000 | R8 HIV | bar: Q2 to Q5
11.3 | Explore the use of NVP dispersible tablets to replace oral solutions in PMTCT. | [11 empty] | Activities for introduction of NVP described |  | PMUs | NACP | 1000 | R8 HIV | Other HIV partners | bar: Q1 to Q2
11.4 | Support the change from NVP oral towards dispersible tabs | [11 empty] | Results documented |  | NACP/PMU | PRA | 5000 | R10 HIV | Other HIV partners | bar: Q2 to Q5
11.4 | Verify the need for additional information & training at the introduction of scored tablets such as EFV 200mg. | [11 empty] | Activities for introduction of Efavirenz scored tabs described |  | PMUs | PRA/NACP | 1000 | R8 HIV | bar: Q1
11.5 | Implement activities identified to support the introduction of EFV | [11 empty] | Results documented |  | NACP/PMU |  | 10000 | R10 HIV | bar: Q1 to Q2
11.6 | Update the national formulary with regard to drugs related to the three diseases, dissiminate and proivde specific training | [11 empty] | NF updated |  | PRA | PMU/Therapeutic committee | 76000 | R7,8 and 10 | bar: Q1 to Q2; Q8
11.6.1 | Prepare information on recent protocols for treatment | [11 empty] | Documentation recent protocols |  | PRA | PMU/Therapeutic committee | 4000 | R7 TB | bar: Q1 to Q2; Q6 to Q7
11.6.2 | Discuss new developments on standard treatment protocols in the therapeutic comittee meetings. | [11 empty] | Meeting reports |  | PRA | PMU/Therapeutic committee | 8000 | R4 R7 | bar: Q2; Q7
11.6.3 | Format the information for inclusion in the national formulary | [13 empty] | PRA | PMU/Therapeutic committee | 4000 | R4 R7 | bar: Q2; Q7
11.6.4 | Prepare, dissiminate and pronote information and trainings of health staff on recent treatment protocols | [11 empty] | Number of health staff reached |  | PRA | PMU/Therapeutic committee | 30000 | R4 R7 | bar: Q2 to Q4; Q7 to Q8
11.6.5 | Printing of NF new version and or addendum (participation) | [11 empty] | Number of NF distributed | 2000 copies target | PRA | PMU/Therapeutic committee | 30000 | R7 R8 R10 | bar: Q2 to Q3; Q8
11.7 | Identify other areas where increased RDU is required, activities to improve RDU and implement these activities | [11 empty] | Each activity desribed |  | Nat programs | QA task force | 50000 | R10 HIV | bar: Q2 to Q8
12 | Capacity development | [9 empty] | QA task force formed, team build and trained | Capacity build in a number of QA PSM areas |  |  |  |  | 399500
12.1 | Support MSL activities for CD of PSM at district level | [11 empty] | MSL capacity building unit operational and used
12.1.1 | Assist in the equipment of the training facilities with furniture and IT equipment | [11 empty] | Supplies provided in time |  | UNDP | MSL | 77000 | R8 HIV | Already in PSM plan | bar: Q0 to Q1
12.1.2 | Collect data on past et planned logistics trainings, coordinate efforts to improve efficiency and avoid duplication of efforts | bar: Q1 to Q3; Q5; Q7
12.1.3 | Indentify areas for collaboration for CD improved QA in PSM of GF commodities between MSL and UNDP/CHAZ | [11 empty] | MSL CD unit used beyond MSL direct needs only. |  | PMU | MSL | 0 | bar: Q1 to Q2
12.2 | Assist in building a QA team/taskforce | [11 empty] | QA task force motivated and trained |  | PMU | QA task force | 0
12.2.1 | Promote the establishment of the task force and organise regular meetings | [11 empty] | Meeting minutes |  | QA task force | PMU | 7500 | R4 R8 R10 | bar: Q0 to Q1; Q3; Q5; Q7
12.2.2 | Organize a QA training on subjects as preparation of sampling plans, sampling of pharma, principles of pharmacovigilance, inspection of storage facilities.. | [11 empty] | QA training summary |  | QA task force | PMU & PSO | 20000 | R4 R8 | bar: Q0
12.3 | Participate in PSO annual seminar and propose presentations/training sessions (20 national participants 5 days in-country) | [11 empty] | Number of Zambian participants in PSO training seminar |  | QA task force | PMU & PSO | 20000 | R8 | bar: Q2; Q5
12.4 | Promote large participation in UNDP introduction to PSM on line training | [11 empty] | On line trained contributed to basic PSM and QA knowledge |  | QA task force | PMU & PSO | 0 | bar: Q0 to Q1
12.5 | Assist in the development of national QC testing facilities | [11 empty] | CD plan and pathway towards Iso certification for national QC lab available |  | PMU & PSO | QA task force | 0
12.5.1 | Analysis of the options for in-country QC testing for the public sector (Nat lab, MSL, collaboration, cost benefit analysis, conflict of interest, feasibility ...) | [13 empty] | PMU UNDP/PSO | PRA, MSL, CHAZ | 0 |  | see below | bar: Q0 to Q1
12.5.2 | Provide TA for the development of an action plan towards WHO prequalification or Iso certification of a national QC laboratory | [13 empty] | PMU UNDP/PSO | PRA, MSL, CHAZ | 25000 | R4 R8 | bar: Q1
12.5.3 | Support the above developed action plan | [11 empty] | Funds mobilized and plan implemented progressivly |  | PMU | PRA, MSL, + partners | 250000 | R10 HIV | 10.000 R10HIV remaining R11 | bar: Q1 to Q8
13 | Monitoring & Evaluation | [9 empty] | QA plan implemented and documented | QA plan owned by the QA task force |  |  |  |  | 10000
13.1 | As per 12.2.1 + ensure budgets are secured in the GF grants and advocate for funding for QA activities in budgets of other donors | [11 empty] | QA funds mobilised beyond GF grant funding |  | PMU | QA task force | 6000 | R8 and 10 HIV | bar: Q1; Q3; Q5; Q7
13.2 | Monitor progress of the QAP and report to the QA task force | [11 empty] | Regular monitoring reports available |  | PMU |  | 0 | bar: Q1; Q3; Q5; Q7
13.3 | Update the QA plan | [11 empty] | QA plan updated each year |  | PMU | QA task force | 4000 | R8 and 10 HIV | bar: Q3; Q7
[16 empty] | Total US $ | 1923000

## Sheet1
Grant QA budgets | Budget US$
R4 HIV |  | 0.13114 | R4 HIV
R8 HIV | 248247 | 32554.3668 | R8 HIV
R10 HIV | 426742 | 55961.6657 | R10 HIV
R7 TB | 42842 | 5618.1714 | R7 TB
R7 Mal | 86239 | 11309.1237 | R7 Mal
Total | 804070 | 112000 | Total
105443.4587