## Slide 1
NATIONAL SUPPLY CHAIN ASSESSMENT (NSCA2.0) STAKEHOLDER TRAINING
Day 2: Stakeholder Engagement
--:--am/pm : --:--am/pm
--/--/----
USAID Global Health Supply Chain Program - Technical Assistance - National Supply Chain Assessment Task Order

## Slide 2
  Identifying Stakeholders
  Early Stakeholder Engagement
  Sustaining Stakeholder Engagement
  Team and Stakeholder Communications
  Stakeholder Meeting and Training Logistics
Stakeholder Engagement Outline

## Slide 3: Stakeholder Landscape
Notes: Bilateral and Multilateral External Donors are important because of there involvement with the Ministry.
The NSCA 2.0 approach promotes ownership and engagement of country leadership early in the preplanning phase. Implementation is designed to be collaborative – incorporating local policy-makers, health supply chain managers, donors, and other stakeholders. It is expected that the leadership team will collaborate in defining the goals, purpose, and desired outcomes of the assessment based on local needs and plans. This exercise also enables the leadership team to gain a good understanding of the assessment process.

## Slide 4: Stakeholders - Introduction
Stakeholders support and collaboration are critical to ensure the success of the NSCA
A critical early step in planning is identifying the key stakeholders for the assessment
Early and sustained engagement of identified stakeholders is important to ensure smooth execution and foster country ownership
Effective team and stakeholder communications guided by a communications strategy or plan is needed to ensure continuous collaboration among stakeholders
Outline time and other requirements for stakeholder meetings, workshops and trainings
Notes: Once stakeholders have been identified and agree to participate, brief them on the project. This effort is important not only for smooth assessment execution, but also to promote country ownership of the assessment. The goal is to engage all participants in collaborative planning activities so all voices are heard and the assessment meets the needs of the country engaging in the assessment process.
Communication strategy should target the agency or stakeholder as appropriate. This engagement should be clear from the outset of implementation.

## Slide 5: Early Stakeholder Engagement
It is imperative to involve stakeholders in the planning process from the outset and to ensure that the assessment caters to country needs and requirements.
Early stakeholder discussion should address the following:
Overview of NSCA 2.0
Objectives and Purpose of Assessment
Expected outcomes and relevance to country supply chains
Agree on timelines and dates for implementation including data collection
Agree on the review and approval process for stakeholders (MOH and funders of the assessment)
Plan Stakeholder workshop and routine meetings
Notes: Early stakeholder discussion(s) should address the following key areas of the planning process:
Overview of the NSCA 2.0
Review the objective(s) of the assessment and the context for why the assessment is being launched
Describe expected outcomes of the assessment and how they are relevant to the overall health supply chain system
Outline the expected role(s)/contributions for each stakeholder or participating organization
Review timelines and identify dates to complete implementation and data collection activities
Plan for the stakeholders’ workshop
Finalize a series of set stakeholder meetings throughout the assessment

## Slide 6: Team and Stakeholder Communications
A communication strategy needs to be developed to foster stakeholder engagement.
Preferred media or platform for communication must be sought and agreed with and among the stakeholders, including the government. These agreed media or platform will be used to share critical NSCA information and must be updated throughout the assessment.
Clearly delineate roles and responsibilities for communication with key stakeholders within the NSCA team.
Assessment coordinator is tasked with providing regular updates to the assessment team members and stakeholders.
Notes: An important element of the assessment implementation process includes not only identifying stakeholders early on, but also keeping them engaged throughout the assessment process. In the planning and preparation phase, the stakeholder(s) need to commit to ongoing engagement throughout the assessment. Additional activities, meetings, or requirements may be identified and agreed upon as appropriate for the context. The presence of these intermittent engagement activities ensures that stakeholders participate and contribute to all stages of the assessment process.